## Aggregate A and B Data 122220
State | Total Cost ($M) est. | # of projects
CA | 1616.44 | 23
CT | 728 | 3
DC | 608 | 1
IL | 5125.02 | 364
MA | 775 | 3
MN | 55.27 | 18
NV | 200 | 1
NY | 2881.92 | 23
PA | 25 | 1
State Total | 12014.65 | 437
Chicago | 871.9 | 76
Grand Total | 12886.55 | 513

## Attach A - States
PLA PROJECTS APPROVED BY THE FHWA (CY 2009 to December 22, 2020)
ID # | # | State | County | State Contract # | Description | Cost (M) est. | Approved** | Advertise | Letting | Award | Award Cost (M) | Column3 | Omisison Reason
1 |  | IL | Bureau | 66908 | Resurface 7.5 miles of I-80 | 30.4 | 2009-10-16 | 2009-10-02 | 2009-11-06 | 2009-12-21 | 22.2 |  | Pre-May 7, 2010 guidance
2 |  | IL | Madison | 76323 | Reconstruct 3.5 miles IL-255 new alignment | 22 | 2010-01-27 | 2010-01-29 | 2010-03-05 | 2010-04-22 | 21.9 |  | Pre-May 7, 2010 guidance
3 |  | IL | Madison | 76830 | Widen and resurface IL-159 | 8.9 | 2010-02-03 | 2010-05-07 | 2010-06-11 | 2010-07-20 | 9.4 |  | Pre-May 7, 2010 guidance
4 |  | IL | St. Clair | 76D61 | Construct I-70 Mississippi River Bridge | 60 | 2010-03-17 | 2010-04-09 | 2010-05-14 | 2010-06-25 | 46.3 |  | Pre-May 7, 2010 guidance
5 |  | NY | Westchester | D261390 | Construct 5 bridges on I-287 @ Exit 8 | 54 | 2010-03-25 |  | 2010-03-31 | 2010-07-21 | 53 |  | Pre-May 7, 2010 guidance
|  | IL | Madison | 76311 | Construct 3.2 miles of US-67/IL-267 | 23 | 2010-05-06 | 2010-05-07 | 2010-06-11 | 2010-08-20 | 21.4 |  | Pre-May 7, 2010 guidance
|  | IL | Madison | 76318 | Construct 2.0 miles of US-67 | 27 | 2010-05-06 | 2010-06-25 | 2010-07-30 | 2010-10-01 | 20.4 |  | Pre-May 7, 2010 guidance
| 1 | IL | St. Clair | 76C44 | Construct I-70 Mississippi River Bridge | 42 | 2010-05-26 | 2010-06-25 | 2010-07-30 | 2010-09-13 | 28.6
| 2 | IL | Grundy | 66408 | Reconstruct I-80/Brisbane Road interchange | 20 | 2010-07-29 | 2010-08-13 | 2010-09-17 | 2010-10-26 | 18.9
| 3 | IL | Madison | 76C93 | Resurface 11.3 miles of I-55 | 30 | 2010-07-29 | 2010-08-13 | 2010-09-17 | 2010-10-06 | 42.3
| 4 | IL | Rock Island | 64815 | Reconstruct I-280 | 23.1 | 2010-09-21 | 2010-12-10 | 2011-02-21 | 2011-02-15 | 22.4
| 5 | IL | St. Clair | 76882 | Rehab IL-3 Union Pacific RR & Prairie DuPont Canal Bridge | 20 | 2010-09-21 | 2011-03-25 | 2011-04-29 | 2011-06-10 | 14.5
1 | 6 | IL | Jefferson | 78172 | Reconstruct 4.16 m of I-57/64 @ Mt Vernon | 29.3 | 2011-03-17 | 2011-03-25 | 2011-04-29 | 2011-05-10 | 30.6
2 | 7 | NY | Orange | D261655 | Reconstruct/replace bridge on Rt 17/Exit 122 | 72.3 | 2011-03-31 |  | 2011-03-24 |  |  |  | Contract voided 3/1/12
3 | 7 | IL | Cook | 60999 | Rehab I-55 (Stevenson Expressway) bridge | 40.6 | 2011-05-16 | 2011-05-13 | 2011-06-17 | 2011-08-25 | 37.7
4 | 8 | IL | Effingham | 74299 | Reconstruct 2.8 miles I-57/I-70 | 35 | 2011-05-16 | 2011-05-13 | 2011-08-01 | 2012-02-10 | 41.5
5 | 9 | IL | Madison | 76A91 | Replace I-270 bridge | 100 | 2011-05-16 | 2011-05-13 | 2011-06-17 | 2011-07-19 | 104
6 | 10 | IL | Dupage | 60477 | Reconstruct IL-53 | 44.9 | 2011-06-14 | 2011-05-13 | 2011-06-17 | 2011-08-08 | 45.5
7 | 11 | IL | Winnebago | 64813 | Reconstruct IL-2 | 30 | 2011-06-14 | 2011-05-13 | 2011-06-17 | 2011-09-12 | 20.9
8 | 12 | IL | Morgan | 72667 | Reconstruct US-67 | 51.5 | 2011-06-14 | 2011-05-13 | 2011-06-17 | 2011-07-26 | 39.6
9 | 13 | NY | Westchester | 8110.13 | Replace Crane Road Bridges over Bronx River & Metro North RR in Greenburgh & Scarsdale | 46 | 2011-09-26 |  | 2011-10-17 |  | 47
10 | 14 | IL | Kendall | 66671 | Reconstruct IL-47 | 45 | 2011-10-06 | 2011-10-14 | 2011-11-18 | 2012-01-10 | 29.4
11 | 15 | IL | Bureau | 66686 | Reconstruct I-80 | 17.8 | 2011-10-06 | 2011-10-14 | 2011-11-18 | 2012-01-26 | 18.8
12 | 16 | IL | Whiteside | 64B80 | Replace IL-40 Bridge | 21.5 | 2011-10-19 | 2011-10-14 | 2011-11-18 | 2011-12-15 | 27
13 | 17 | IL | Henderson | 68083 | Reconstruct IL-94 | 2.6 | 2011-11-01 | 2011-10-14 | 2011-11-18 | 2011-12-13 | 2.5
14 | 18 | IL | Henderson | 68298 | Replace Carman Rd Bridge over Honey Creek | 2.1 | 2011-11-01 | 2011-10-14 | 2011-11-18 | 2011-12-13 | 2.1
15 | 19 | IL | McDonough | 68A40 | Construct US-136 bridge over IL-336 | 6 | 2011-11-01 | 2012-03-23 | 2012-04-27 | 2012-05-25 | 4.5
16 | 20 | IL | Tazwell | 68370 | Reconstruct IL-8 | 19.1 | 2011-11-15 | 2012-02-03 | 2012-03-09 | 2012-04-03 | 10.2
17 | 21 | IL | DuPage/Kane | 62410 | IL-64 new lane (3.55 miles), bridge rehab | 37.4 | 2011-11-22 | 2011-12-09 | 2012-01-20 | 2012-03-19 | 39.6
18 | 22 | IL | Williamson | 78182 | Reconstruct I-57/IL-13 interchange | 45 | 2011-11-22 | 2011-12-09 | 2012-01-20 | 2012-02-10 | 40.5
19 | 23 | IL | Kane & DuPage | 60I22 | Reconstruct IL-38 | 32.9 | 2011-11-22 | 2012-06-29 | 2012-08-03 | 2012-10-10 | 25.8
20 | 24 | IL | Winnebago | 64C29 | Reconstruct I-90 | 48.2 | 2011-11-22 | 2011-12-09 | 2012-01-20 | 2012-03-07 | 33.8
21 | 25 | IL | Lake | 62187 | Reconstruction of IL-176 | 4.4 | 2011-11-28 | 2012-02-03 | 2012-03-09 | 2012-04-16 | 3.7
22 | 26 | IL | Kendall | 66985 | Reconstruct US-34 | 15.5 | 2011-11-28 | 2011-12-09 | 2012-01-20 | 2012-04-09 | 15.2
23 | 27 | IL | Shelby | 74467 | Rehab I-57 Effingham-Shelby County Line to US-45 (8.7 miles) | 14 | 2011-11-28 | 2011-12-09 | 2012-01-20 | 2012-02-09 | 11
24 | 28 | IL | Jackson | 78049 | Reconstruct IL-4 | 3.4 | 2011-11-28 | 2011-12-09 | 2012-01-20 | 2012-02-06 | 4.2
25 | 29 | IL | Cook | 60M79 | Reconstruction of I-90 | 3.4 | 2011-11-28 | 2011-12-09 | 2012-01-20 | 2012-03-20 | 3.9
26 | 30 | IL | Cass | 72B55 | Reconstruct IL-78 | 2.9 | 2011-11-28 | 2011-12-09 | 2012-01-20 | 2012-02-09 | 2.7
27 | 31 | IL | Sangamon | 72F01 | Reconstruct I-72 | 2.7 | 2011-11-28 | 2011-12-09 | 2012-01-20 | 2012-02-09 | 2
28 | 32 | IL | Wayne | 74216 | Reconstruct IL-15 bridge | 3.9 | 2011-12-01 | 2011-12-09 | 2012-01-20 | 2012-02-09 | 2.7
29 | 33 | IL | St. Clair | 76884 | Replace IL-15 bridge | 18.9 | 2011-12-01 | 2011-12-09 | 2012-01-20 | 2012-04-27 | 14.4
30 | 34 | IL | Jasper | 94437 | Reconstruct IL-33 | 15 | 2011-12-01 | 2012-02-03 | 2012-03-09 | 2012-04-03 | 14.9
31 | 35 | IL | St. Clair | 76415 | Resurface/Rehab I-64 | 12 | 2011-12-07 | 2011-12-09 | 2012-01-20 | 2012-02-10 | 13
32 | 36 | IL | Madison | 76B80 | Rehab 4.3 miles IL-140/IL-111 | 5.3 | 2011-12-07 | 2011-12-09 | 2012-01-20 | 2012-02-06 | 5.4
33 | 37 | IL | Cook | 62377 | Reconstruct IL-31 & IL-176 | 2.5 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-05-10 | 2.8
34 | 38 | IL | McHenry | 62537 | Reconstruct IL-31 & IL-176 | 12.1 | 2012-01-25 | 2012-03-23 | 2012-04-27 | 2012-06-13 | 10.2
35 | 39 | IL | McDonough | 68691 | US-67 bridge reconstruction | 2.7 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-04-02 | 4
36 | 40 | IL | Tazwell | 68914 | Reconstruct I-155 | 17 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-03-20 | 18.7
37 | 41 | IL | Cumberland | 74252 | Resurface 13 miles IL-121 | 5.8 | 2012-01-25 | 2012-03-23 | 2012-04-27 | 2012-05-24 | 4.6
38 | 42 | IL | Williamson | 78216 | Improve IL-13/Greenbriar Road intersection | 4.2 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-04-03 | 3.7
39 | 43 | IL | Williamson | 98859 | Reconstruct IL-13 over BNSF Railway | 41 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-04-03 | 19.7
40 | 44 | IL | Kane | 60H45 | Reconstruct US-20 @ McLean Blvd | 40 | 2012-01-25 | 2012-03-23 | 2012-04-27 | 2012-06-12 | 34.7
41 | 45 | IL | Jo Daviess | 64C94 | Reconstruct US-20 | 7 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-04-02 | 6.8
42 | 46 | IL | LaSalle | 66A48 | Resurface of I-80 from 0.5 mile east of IL-178 to Fox River Bridge (12.1 miles) | 21.7 | 2012-01-25 | 2012-02-03 | 2012-03-09 | 2012-04-23 | 20.3
43 | 47 | IL | Winnebago | 64515 | Reconstruct IL-2 | 13.5 | 2012-02-29 | 2012-05-11 | 2012-06-15 | 2012-08-21 | 13.4
44 | 48 | IL | Henry | 64G09 | Improve IL-17 and US-34 | 4.9 | 2012-02-29 | 2012-03-23 | 2012-04-27 | 2012-05-17 | 4.4
45 | 49 | IL | Winnebago | 64H72 | Rehab I-39 bridge over Kishwaukee River | 2.8 | 2012-02-29 | 2012-03-23 | 2012-04-27 | 2012-05-17 | 2.6
46 | 50 | IL | Edwards | 74247 | Resurface 13 miles of IL-130 | 5.1 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-07-13 | 5.7
47 | 51 | IL | Fulton | 88795 | Reconstruct US-24 | 6.4 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-07-19 | 8
48 | 52 | IL | DuPage | 60P41 | Replace pump station/IL-59 Improvements | 4 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-08-02 | 6.6
49 | 53 | IL | Will | 60T40 | Reconstruction of I-57 | 5.2 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-07-13 | 4.2
50 | 54 | IL | Peoria | 68A30 | Reconstruction of IL-6 | 2.1 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-07-30 | 2
51 | 55 | IL | St. Clair | 76D06 | Reconstruct intersection at IL-15/158 | 5.5 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-07-30 | 4.7
52 | 56 | IL | Marion | 76F90 | Resurface 18.7 miles of I-57 | 17.1 | 2012-04-26 | 2012-05-11 | 2012-06-15 | 2012-07-20 | 15.4
53 | 57 | IL | Christian & Sangamon | 72829 | Reconstruction of IL-29 | 50 | 2012-04-30 | 2012-05-11 | 2012-06-15 | 2012-07-30 | 41.7
54 | 58 | IL | Christian | 72E12 | IL-104 Bridge & Lane Rehab - Pawnee to Auburn | 3.4 | 2012-04-30 | 2012-05-11 | 2012-06-15 | 2012-07-13 | 3
55 | 59 | IL | Henry,Rock Island,Whiteside | 64H77 | I-74, I-80, I-88 & I-280 safety improvements | 4.9 | 2012-04-30 | 2012-05-11 | 2012-06-15 | 2012-07-18 | 2
56 | 60 | IL | Saline | 78290 | Resurface 2.84 miles of IL-34 | 3 | 2012-05-01 | 2012-03-23 | 2012-06-15 | 2012-06-27 | 2.5
57 | 61 | CA | Los Angeles | HD-7961 | Reconstruct Gerald Desmond Bridge (Ocean Blvd) in Port of Long Beach D-B | 1000 | 2012-06-19
58 | 62 | MA | Suffolk & Middlesex | 72699 | Longfellow Bridge Rehab D-B project | 260 | 2012-06-21 | 2012-08-28 | 2013-01-30 | 2013-02-27 | 255.5
59 | 63 | IL | Kendall | 60I32 | Reconstruct US-30 Briarcliff Rd to US-34 (2.4 miles) | 25.478 | 2012-06-25 | 2012-08-17 | 2012-09-21 | 2013-01-22 | 22.342
60 | 64 | IL | Kane/ Kendall | 60I33 | Reconstruction US-30 at IL 31 & BNSF RR (0.8 miles) | 21.33 | 2012-06-25 | 2012-08-17 | 2012-09-21 | 2013-03-06 | 21.175
61 | 65 | IL | Lake | 60L77 | Reconstruct I-94 WI state line to IL-173 (2.61 miles) | 35.9 | 2012-06-25 | 2012-06-29 | 2012-08-03 | 2012-10-23 | 29.2
62 | 66 | IL | Williamson | 78203 | Add lanes in each direction on IL‐13 | 4 | 2012-06-26 | 2012-10-05 | 2012-11-09 | 2012-12-10 | 3.2
63 | 67 | NY | Rockland & Westchester | D214187 | Tappan Zee Hudson River Crossing (I-87/I-287) Design-Build |  | 2012-07-11 | 2012-03-09 | 2012-12-17 | 2013-01-18 | 3142
64 | 68 | NY | Orange | D262058 | Reconstruct/replace bridge on Rt 17/Exit 122 | 70.6 | 2012-07-13
65 | 69 | IL | Cook | 60M57 | IL-83 Signalization Improvements (Kedzie Ave to Western Ave) | 10.438 | 2012-08-10 | 2012-08-17 | 2012-09-21 | 2012-12-17 | 22.15
66 | 70 | IL | Kane | 60P65 | Rehab IL-31 and Mooseheart RD Intersection | 2.4 | 2012-08-10 | 2012-10-05 | 2012-11-09 | 2013-04-30 | 1.986
67 | 71 | IL | Lee/Ogle/ Stephenson | 64H76 | Safety upgrades along various routes (I-39/ US-20) | 2.2 | 2012-08-10 | 2012-08-17 | 2012-09-21 | 2012-10-11 | 1.282
68 | 72 | IL | Greene | 76F25 | Resurface 6.65 miles of US-67 | 2.4 | 2012-08-10 | 2012-08-17 | 2012-09-21 | 2012-11-02 | 2.184
69 | 73 | IL | St. Clair | 76F69 | IL-3 Bridge Construction under MLK approach bridges north of Riverpark Drive | 2 | 2012-08-10 | 2012-08-17 | 2012-09-21 | 2013-04-05 | 1.847
70 | 74 | IL | Tazwell | 68620 | Reconstruct the I‐74/I‐155 interchange | 85 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2013-03-06 | 86.6
71 | 75 | IL | Champaign | 70109 | Replace bridge on I‐70 | 2.7 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-10 | 2.4
72 | 76 | IL | Vermilion | 70967 | Replace medial cable barrier on I‐74 | 2.3 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-05 | 2
73 | 77 | IL | Vermillion | 70968 | Replace medial cable barrier on I‐74 | 2.7 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-05 | 2.4
74 | 78 | IL | Cumberland | 74416 | Replace 4 substructures on I‐70 | 30.6 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-05 | 21.3
75 | 79 | IL | Cumberland | 74466 | Rehabilitate 7.2 miles on I‐70 | 7 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-18 | 10.2
76 | 80 | IL | Pulaski & Union | 78289 | Reconstruct of I‐57 | 6.3 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-10 | 6.2
77 | 81 | IL | Vermillion | 90939 | Widen & resurface US-36 | 6.2 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-20 | 6.9
78 | 82 | IL | Stephenson | 64E76 | Remove/replace deck of bridge over CC&P RR | 2.7 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2012-12-05 | 2.1
79 | 83 | IL | Kane | 60A95 | Improve an intersection on IL‐31 | 2.8 | 2012-09-28 | 2012-10-05 | 2012-11-09 | 2013-02-25 | 3
80 | 84 | IL | DuPage | 60P42 | Construct 5 concrete retaining walls on IL‐59 | 5.4 | 2012-09-28 | 2013-05-14 | 2013-05-24 | 2013-07-17 | 5.2
81 | 85 | IL | Cook | 60T35 | Widen/reconstruct Willow Road | 22.7 | 2012-09-28 | 2012-12-07 | 2013-01-18 | 2013-02-13 | 27.2
82 | 86 | MA | Essex | 73274 | Replace I-95 Whittier Bridge D-B project | 285 | 2012-10-25 | 2012-09-27 | 2013-02-21 | 2013-02-27 | 292.1
83 | 87 | IL | St. Clair | 76F70 |  | 2.3 | 2012-11-23 | 2012-12-07 | 2013-01-18 | 2014-07-22 | 1.5 |  | STA funded
84 | 87 | IL | Kendall | 66420 | Reconstruct IL-71 | 24 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-04-03 | 21.4
85 | 88 | IL | Livingston | 66752 | Resurface IL-116 | 2.5 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2014-08-21 | 2.4 |  | STA funded
86 | 88 | IL | Henderson | 68409 | Reconstruct US-34 | 50 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-05-02 | 40.5
87 | 89 | IL | Peoria | 68883 | Replace I‐474 bridge deck @ Maxwell Road | 4 | 2012-12-03 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 2.2
88 | 90 | IL | McLean | 70783 | Resurface US-136 | 2.1 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-02-05 | 2.1
89 | 91 | IL | Christian | 72961 | Reconstruct US-51 | 39 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-02-27 | 27.6
90 | 92 | IL | Macon | 74156 | Resurface 10.7 miles of IL-48 | 4.3 | 2012-12-03 | 2013-02-01 | 2013-03-08 | 2013-05-22 | 4.3
91 | 93 | IL | Effingham & Clay | 74450 | Resurface I‐57 | 9.2 | 2012-12-03 | 2013-02-01 | 2013-03-08 | 2013-07-08 | 7.6
92 | 94 | IL | Coles | 74511 | Resurface US-45 | 4.2 | 2012-12-03 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 3.3
93 | 95 | IL | Clay | 74513 | Resurface Old US-50 | 2.1 | 2012-12-03 |  | 2013-01-18 |  |  |  | Withdrawn
94 | 95 | IL | Shelby & Moultrie | 74552 | IL-128 safety improvements | 2.7 | 2012-12-03 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 3.3
95 | 96 | IL | St. Clair | 76848 | Construct .2 miles I-3 on new alignment | 22.5 | 2012-12-03 | 2013-05-14 | 2013-05-24 | 2013-11-06 | 18.3
96 | 97 | IL | Lawrence | 94977 | Resurface IL-1 | 3.6 | 2012-12-03 | 2013-05-10 | 2013-06-14 | 2013-07-18 | 4
97 | 98 | IL | Cook | 60G37 | Reconstruct US-12 | 29.2 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-05-06 | 37.5
98 | 99 | IL | DuPage | 60I31 | Replace IL-59 bridge | 20.4 | 2012-12-03 | 2013-05-10 | 2013-06-14 | 2013-07-10 | 25.9
99 | 100 | IL | Kane | 60N13 | Replace I-47 bridge over Virgil Ditch | 2.3 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-02-13 | 1.7
100 | 101 | IL | Cook | 60P35 | Reconstruct US-12 | 19 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-05-07 | 21.5
101 | 102 | IL | Cook | 60T33 | Resurface I‐190 | 10 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-02-13 | 4.9
102 | 103 | IL | Will | 60V41 | Reconstruct I‐57 | 6.1 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-04-22 | 5.9
103 | 104 | IL | Henry | 64F25 | Remove/replace culverts | 2.9 | 2012-12-03 | 2013-10-04 | 2013-11-08 | 2013-12-12 | 2.9
104 | 105 | IL | Sangamon | 72F23 | Resurface IL-4 & IL-97 | 2.7 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-02-25 | 2.7
105 | 106 | IL | Cass | 72F69 | IL-125 | 5.6 | 2012-12-03 | 2013-03-22 | 2013-04-26 | 2013-05-22 | 5.5
106 | 107 | IL | Cass | 72F70 | Resurface IL-78 | 2.3 | 2012-12-03 | 2012-12-07 |  |  |  |  | STA funded
107 | 108 | IL | Menard | 72F71 | Resurface IL-97 | 2.2 | 2012-12-03 | 2012-02-07 |  |  |  |  | STA funded
108 | 107 | IL | Madison | 76A89 | Resurface I‐255 | 18.7 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-02-25 | 15.5
109 | 108 | IL | Monroe | 76F51 | Widen IL-3 & reconstruct Vanderbrook Drive | 3.4 | 2012-12-03 | 2012-12-07 | 2013-01-18 | 2013-06-06 | 3.7
110 | 109 | IL | Rock Island | 64341 | Replace US-6 Shaffer Creek bridge & reconstruct Niabi Zoo Road | 2.8 | 2013-01-28 | 2013-04-16 | 2013-04-26 | 2013-05-22 | 3.8
111 | 110 | IL | Winnebago | 64750 | Reconstruct US-20/Rte 303 (West State St) | 8.5 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-04-12 | 8.5
112 | 111 | IL | Winnebago | 64821 | Resurface/widening/curbing IL-2 | 18.5 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-05-03 | 19
113 | 112 | IL | Alexander | 78344 | US-51/IL-3 | 2 | 2013-01-28 | 2013-03-22 | 2013-04-26 | 2013-05-28 | 1.3
114 | 113 | IL | Adams | 72E31 | US-24/IL-96 | 3.1 | 2013-01-28 | 2013-03-22 | 2013-04-26 | 2013-05-28 | 2.4
115 | 114 | IL | Cook | 60J14 | Reconstruct IL-171 bridge over I-90 | 16 | 2013-01-28 | 2013-04-16 | 2013-04-26 | 2013-05-28 | 20.8
116 | 115 | IL | DuPage | 60R30 | Reconstruct IL-59 (segment A) | 30 | 2013-01-28 | 2013-05-14 | 2013-05-24 | 2013-07-31 | 34.6
117 | 116 | IL | DuPage | 60R31 | Reconstruct IL-59 (segment B) | 25.7 | 2013-01-28 | 2013-05-14 | 2013-05-24 | 2013-07-11 | 24.4
118 | 117 | IL | DuPage | 60T80 | Replace signals @ IL-64/Swift Rd interchange & IL-64/ I-355 ramps | 2.4 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 0.9
119 | 118 | IL | Cook | 60V61 | Reconstruct bridge/ intersection @I-94/Stony Island Feeder | 7 | 2013-01-28 | 2013-04-16 | 2013-04-26 | 2013-05-22 | 10.8
120 | 119 | IL | Cook | 60W07 | Reconstruct US-45 (131st to 179st) project - remove median/replace culverts (segment A) | 2 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 1.4
121 | 120 | IL | Cook | 60W09 | Reconstruct US-45 (131st to 179st) project - remove median/replace culverts (segment B) | 2 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 2
122 | 121 | IL | Carroll & Jo Daviess | 64H85 | Pavement Rehab IL-84 in Hanover | 3.9 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2014-06-09 | 3.6
123 | 122 | IL | LaSalle | 66A91 | Resurface I-80 | 10.9 | 2013-01-28 | [5 empty] | Withdrawn
124 | 122 | IL | McDonough | 68A42 | Construct Macomb Bypass (IL-336/IL-110) project - Grading | 34.5 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-07-09 | 33
125 | 123 | IL | Sangamon | 72C90 | Road resurfacing | 13.2 | 2013-01-28 | 2013-12-06 | 2014-01-17 | 2014-03-03 | 14.8
126 | 124 | IL | Hancock | 72F32 | Resurface IL-9/IL-96 | 2.6 | 2013-01-28 | 2013-02-01 |  |  |  |  | STA funded
127 | 125 | IL | Logan | 72F77 | Resurface IL-54 | 3.1 | 2013-01-28 | [5 empty] | Withdrawn
128 | 124 | IL | Madison | 76F27 | Resurface 7.85 miles IL-143 | 2.6 | 2013-01-28 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 2
129 | 125 | IL | Iroquois | 66944 | Road profiling & bridge replacements I-57 | 5.2 | 2013-02-01 | 2013-02-01 | 2013-03-08 | 2013-04-02 | 5.8
130 | 126 | IL | Mason | 72E03 | Road resurfacing/Shoulder repair | 2.9 | 2013-02-01 | 2013-05-10 | 2013-06-14 | 2013-07-10 | 2.9
131 | 127 | IL | St. Clair | 76E89 | IL-13 resurfacing | 2.4 | 2013-03-06 | 2013-03-26 | 2013-04-26 | 2013-06-07 | 1.1
132 | 128 | IL | Cook | 60F05 | US-45; add lane (2.80 miles) | 19.4 | 2013-03-06 | 2013-03-26 | 2013-04-26 | 2013-07-25 | 29.7
133 | 129 | IL | Will | 60L69 | Reconstruct I-57 | 17.7 | 2013-03-06 | 2013-06-28 | 2013-08-02 | 2014-04-14 | 28.9
134 | 130 | IL | Cook | 60M61 | US-45 add lane (1.93 miles) | 16.4 | 2013-03-06 | 2013-03-26 | 2013-04-26 | 2013-07-03 | 26.9
135 | 131 | IL | Cook | 60M62 | US-45 1.79 add lane (miles) | 25.6 | 2013-03-06 | 2013-03-26 | 2013-04-26 | 2013-07-08 | 32.9
136 | 132 | IL | Madison | 76B85 | IL-159 widening | 11.5 | 2013-03-09 | 2013-04-26 | 2013-05-24 | 2013-07-08 | 11.8
137 | 133 | IL | Rock Island & Henry | 64D23 | Replace I-74/280 bridges over Coal Creek | 20.1 | 2013-03-22 | 2013-04-16 | 2013-04-26 | 2013-05-22 | 17.7
138 | 134 | IL | Winnebago | 64J23 | Pavement Rehab on US Bus 20 in Rockford | 3.3 | 2013-03-22 | 2013-04-16 | 2013-04-26 | 2013-05-21 | 2.3
139 | 135 | CA | Contra Costa | 0662-6R4101-14 | Reconstruct Alhambra Valley Road | 1.4 | 2013-04-02
140 | 136 | CA | Contra Costa | 0662-6R4255-10 | Vasco Rd Safety Improvements - Phase II | 10.6 | 2013-04-02
141 | 137 | IL | Clinton | 76479 | Bridge Construction | 14.5 | 2013-04-12 | 2013-03-22 | 2013-04-26 | 2013-06-07 | 10.6
142 | 138 | IL | Monroe | 76817 | Widening IL-3 to 5 lanes/Intersection Improvement at IL-156/Lakeview Drive | 25.6 | 2013-04-12 | 2013-05-10 | 2013-06-14 | 2013-07-26 | 17.6
143 | 139 | IL | Perry | 78351 | Resurface 11.7 miles of IL-154 | 2.8 | 2013-05-08 | 2013-04-19 | 2013-05-24 | 2013-06-27 | 3
144 | 140 | IL | Iroquois | 66757 | Road patching & bridge replacements I-57 | 14.2 | 2013-05-09 | 2013-02-01 | 2013-06-14 | 2014-08-26 | 14.7 |  | STA funded
145 | 140 | IL | Grundy | 66873 | Replacement of I-80 Bridge over Minooka Rd | 6.3 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 7
146 | 141 | IL | Iroquois | 66942 | Replacement of I-57 Bridge over Old IL-45 | 5.8 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 6
147 | 142 | IL | Peoria | 68614 | Resurface US-150 | 4.2 | 2013-05-09 | 2013-07-19 | 2013-08-02 | 2014-01-22 | 3.1
148 | 143 | IL | Tazwell | 68757 | Replacement of IL-9 Bridge over Mud Creek | 2.3 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 2.3
149 | 144 | IL | Champaign | 70700 | Replace Bridge on I-74 | 5.5 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 4.3
150 | 145 | IL | Richland | 74409 | Bridge & Pavement Repairs on IL-130 | 4.8 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 4.5
151 | 146 | IL | Shelby | 74474 | Resurface IL-16 | 4.3 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 3.1
152 | 147 | IL | Macon | 74537 | Resurface IL-48 | 5.5 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-09 | 5.5
153 | 148 | IL | St. Clair | 76850 | Paving newly constructed IL-3 | 12.2 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-10 | 3.6
154 | 149 | IL | Williamson | 78258 | Add lane on IL-13 | 10 | 2013-05-09 | 2013-07-19 | 2013-08-02 | 2013-08-30 | 7.9
155 | 150 | IL | White | 78287 | Resurface 9.9 miles of IL-1 | 2.6 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-09 | 2.6
156 | 151 | IL | White | 78305 | Resurface IL-14 | 3 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-09 | 2.4
157 | 152 | IL | Franklin | 78317 | Reconstruct 3 miles of IL-37 | 2.2 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-09 | 2.6
158 | 153 | IL | Logan | 72E11 | Bridge Deck Repair on I-55 | 13.4 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-08-09 | 17.3
159 | 154 | IL | St. Clair | 76E88 | Resurface 6.6 miles of IL-13 | 2.4 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 1.6
160 | 155 | IL | Cook | 60F63 | Bridge Replacement on I-94 at Ohio Street | 12.5 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-10 | 16.4
161 | 156 | IL | Cook | 60J12 | Replace I-94/Stony Island Feeder Bridge | 25.1 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-25 | 30
162 | 157 | IL | Boone | 64G97 | Add new lanes on US 2 Business | 3.3 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 3.2
163 | 158 | IL | LaSalle | 66C83 | Repair Shoulders/Add Rumble Strips on I-39 | 3.7 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 3
164 | 159 | IL | LaSalle | 66C98 | Repair Shoulders/Install Rumble Strips on I-39 | 4.5 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 3
165 | 160 | IL | Woodford | 68B24 | Resurface IL-116 | 1.8 | 2013-05-09 | [5 empty] | Withdrawn
166 | 160 | IL | Sangamon | 72C88 | Resurface I-72 | 10 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-25 | 10.9
167 | 161 | IL | Madison | 76D99 | Resurface 2.9 miles I-55 | 17.1 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-09 | 18.4
168 | 162 | IL | Jersey | 76F24 | Resurface & Replace Guardrail on IL-100 |  | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-17 | 3.6
169 | 163 | IL | Randolph | 76F92 | Resurface 6.9 miles of IL-3 |  | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-09 | 3.6
170 | 164 | IL | Madison | 76F97 | IL-270 safety improvements (12.41 mi guardrail) | 2.2 | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 1.7
171 | 165 | IL | Madison | 76G06 | Resurface various intersections along IL-3 |  | 2013-05-09 | 2013-05-10 | 2013-06-14 | 2013-07-08 | 1.8
172 | 166 | IL | Winnebago | 64988 | IL-173 Reconstruction (Alpine to Mitchell) | 22 | 2013-06-17 | 2013-06-28 | 2013-08-02 | 2014-02-04 | 28
173 | 167 | IL | Logan | 72789 | BL I-55 Reconstruction | 13 | 2013-06-17 | 2013-06-28 | 2013-08-02 | 2013-08-22 | 12
174 | 168 | IL | Effingham | 74295 | I-57/70 Reconstruction | 60.5 | 2013-06-17 | 2013-08-16 | 2013-09-20 | 2013-11-04 | 61.6
175 | 169 | IL | Cook | 60W25 | Morgan St Bridge at I-290/Congress Parkway Improvements | 15.1 | 2013-06-17 | 2013-07-19 | 2013-08-02 | 2013-08-22 | 18.5
176 | 170 | IL | Rock Island | 64H11 | IL-92 Widening & Shoulder reconstruction | 5 | 2013-07-09 | 2013-07-19 | 2013-08-02 | 2013-09-16 | 6.2
177 | 171 | IL | Sangamon | 72501 | Reconstruct/Resurface IL-29 | 9 | 2013-08-08 | 2013-08-16 | 2013-09-20 | 2014-03-03 | 9.7
178 | 172 | IL | Cook & DuPage | 60K77 | Reconstruct I-55 Structure over County Line Rd | 6.5 | 2013-08-08 | 2013-08-16 | 2013-09-20 | 2013-10-11 | 7.4
179 | 173 | IL | Cook | 60L70 | I-94 to US-41 reconstr 2 bridges | 61.8 | 2013-08-08 | 2014-12-18 | 2015-01-30 | 2015-03-19 | 73.9
180 | 174 | IL | Cook | 60N18 | Safety Improvements to US-20 | 2.2 | 2013-08-08 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 2.3
181 | 175 | IL | Rock Island | 64B84 | Construct New 41st Drive Bridge over IL-5 | 11 | 2013-08-08 | 2013-10-04 | 2013-11-08 | 2014-01-10 | 16.2
182 | 176 | IL | Rock Island | 64D18 | Replace IL-92 Big Branch Creek Bridge | 2.5 | 2013-08-08 | 2013-08-16 | 2013-09-20 | 2013-11-01 | 1.3
183 | 177 | IL | Carroll | 64D83 | Reconstruction US-52 over Carroll Creek | 3.9 | 2013-08-08 | 2013-08-16 | 2013-09-20 | 2013-10-11 | 4.1
184 | 178 | IL | Kankakee | 66750 | Replace I-57 bridge over Kankakee River | 24 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-18 | 19.3
185 | 179 | IL | Bureau | 66998 | Replace I-80 bridge over Hennepin Canal | 6.5 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 5.2
186 | 180 | IL | Knox | 68759 | Replace IL-97 bridge over the Spoon River | 9.8 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 5.5
187 | 181 | IL | McLean | 70570 | Replacement of I-55 bridge over I-74 | 13.1 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 11.6
188 | 182 | IL | Adams & Pike | 72781 | Reconstruct IL-96 | 5 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2014-04-03 | 5
189 | 183 | IL | Peoria | 88792 | Widen & resurface IL-96 | 6.6 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2014-03-11 | 8.2
190 | 184 | IL | Jo Daviess | 64E08 | Replace US-20 bridge over the Apple River | 3.1 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 5.2
191 | 185 | IL | Cook | 60J11 | Replace IL-64 bridge over Des Plaines River | 8.2 | 2013-09-26 | 2014-01-24 | 2014-02-28 | 2014-04-28 | 9.8
192 | 186 | IL | McHenry | 60V72 | Reconstruct/widen IL-31 | 8 | 2013-09-26 | 2014-01-24 | 2014-02-28 | 2014-04-14 | 5.2
193 | 187 | IL | Cook | 60W26 | Reconstruct I-90/I-94/I-290 interchange | 25 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 42.6
194 | 188 | IL | Winnebago | 64D19 | Replace US-20 Bypass bridge over Rock River | 27 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-20 | 20.8
195 | 189 | IL | Winnebago | 64H70 | Reconstruct IL-2 & Roscoe Rd Intersection | 5.6 | 2013-09-26 | 2014-01-24 | 2014-02-28 | 2014-05-01 | 5.9
196 | 190 | IL | Grundy | 66B83 | Reconstruct IL-47 | 35.6 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-23 | 38.4
197 | 191 | IL | Christian | 72A61 | Reconstruct IL-48 & IL-29 | 2.1 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2013-12-10 | 1.9
198 | 192 | IL | St Clair | 76D22 | Resurface I-64 | 16.4 | 2013-09-26 | 2013-10-04 | 2013-11-08 | 2014-12-18 | 15.3
199 | 193 | IL | Kankakee | 66905 | FAP 41 | 7 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-04-07 | 8.2
200 | 194 | IL | Champaign | 70663 | US-150 roadway improvements for 6 miles | 7 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-05-27 | 6.8
201 | 195 | IL | White | 78282 | Rehab 7.1 miles of I-64 (EB & WB) | 12 | 2013-11-26 | 2013-02-06 | 2014-01-17 | 2014-03-03 | 6.5
202 | 196 | IL | Cook | 60L73 | Reconstruction LaGrange Rd/Joliet Rd Intersection | 4.3 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-03-11 | 4.2
203 | 197 | IL | Lake | 60N22 | Reconstruct IL-132 Over Des Plaines River | 2.2 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-04-01 | 2.5
204 | 198 | IL | Cook | 60V34 | Safety Improvements US 43/IL 171 | 2 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-03-03 | 1.6
205 | 199 | IL | Cook | 60W29 | Peoria St. Bridge @ I-290/Congress Parkway Reconstruction | 17.8 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-04-03 | 23.6
206 | 200 | IL | Madison | 76F10 | Resurface 4.5 miles of I-255 | 17.5 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-03-03 | 17.4
207 | 201 | IL | St Clair | 76G37 | Rehab 8.8 miles of EB IL-15 | 4.2 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-03-03 | 4.88
208 | 202 | IL | St Clair | 76G38 | Rehab 8.8 miles of WB IL-15 | 4.2 | 2013-11-26 | 2013-12-06 | 2014-01-17 | 2014-03-03 | 4.9
209 | 203 | IL | Wayne | 74512 | Resurface US-45 | 3 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 2.4
210 | 204 | IL | Williamson | 78277 | Rehab Herrin Rd | 5.4 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 5.1
211 | 205 | IL | Cook | 60W71 | I-90/94/290 Harrison St. Bridge (east) Rehab | 8.2 | 2014-01-23 | 2014-01-24 | 2014-04-25 | 2014-06-09 | 10.776
212 | 206 | IL | Henry | 64G21 | Pavement Rehab IL-92 | 2.7 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 2.4
213 | 207 | IL | JoDaviess | 64H62 | US-20, Tippett Rd to IL-84 | 2 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 2.1
214 | 208 | IL | Lee/Ogle | 64J29 | Resurface IL-251 from I-88 to Chicago Rd | 3.7 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 3.2
215 | 209 | IL | DeKalb | 66D36 | IL-64 Safety Improvements | 2.4 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 1.7
216 | 210 | IL | Logan | 72B82 | IL-20 Rehab | 5.6 | 2014-01-23 | 2014-01-24 | 2014-02-28 | 2014-04-03 | 3.7
217 | 211 | MN | St Louis | SP-069-733-024 | 11.6 miles resurfacing on CSAH-133 | 4 | 2014-03-13
218 | 212 | CA | Contra Costa | BRLO-5928(045) | Replace Orwood Road Bridge | 5.7 | 2014-03-19
219 | 213 | CA | Contra Costa | BRLO-5928(068) | Replace Marsh Creek Detention Facility Bridge | 1.2 | 2014-03-19
220 | 214 | CA | Contra Costa | BRLS-5928(067) | Replace San Pablo Avenue Bridge | 2.7 | 2014-03-19
221 | 215 | IL | Peoria | 68683 | Allen Rd/Old IL-176 Improvements | 12.935 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 12.356
222 | 216 | IL | Vermilion | 70614 | Replace Bridge on IL-119 | 2.48 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 2.6
223 | 217 | IL | Sangamon | 72890 | Wabash Avenue widening and improvements | 19.5 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 25.588
224 | 218 | IL | Fayette | 74175 | I-70 Bridge Replacement | 47.52 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 19.626
225 | 219 | IL | Shelby & Effingham | 74610 | Safety Improvements on IL-32 from IL-16 to IL-33, 16.7 miles | 3.39 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 2.258
226 | 220 | IL | Williamson | 78221 | New IL-13 interchange & overpass at Wolf Creek Road | 26 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 24.1
227 | 221 | IL | Jefferson | 78276 | I-57/64 pavement rehab & bridge rehab | 8.5 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 12.76
228 | 222 | IL | Saline | 78401 | Remove/Replace NB/SB Lane of IL-34 North of Harrisburg | 3 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 3.27
229 | 223 | IL | Bond | 76D21 | I-70 Resurfacing 4.5 miles & Bridge Repair | 11.4 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 8.53
230 | 224 | IL | Madison | 76G60 | Resurface 4.5 miles of IL-3 | 2.1 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 1.958
231 | 225 | IL | Washington | 76G61 | Resurface 9.86 of IL-177 | 2.8 | 2014-03-24 | 2014-03-21 | 2014-04-25 | 2014-06-09 | 3.1
232 | 226 | IL | Peoria | 68481 | IL-29 | 2 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 1.5
233 | 227 | IL | Peoria | 68697 | IL-8 Reconstruction | 3.15 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 3
234 | 228 | IL | Cumberland | 74386 | I-70 resurfacing 7.5 miles | 5.7 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-08-26 | 2
235 | 229 | IL | Macon | 74475 | IL-128 | 2.79 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 3
236 | 230 | IL | White | 78379 | IL-1 improvements | 3.2 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 3.2
237 | 231 | IL | Cook | 60J15 | Rehab 63rd St Bridge over I90/94 & CTA | 8.3 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 8.3
238 | 232 | IL | Kane | 60T09 | US-20 Intersection Improvements (CMAQ $$) | 2 | 2014-05-06 | 2014-08-12 | 2014-08-22 | 2014-09-03 | 3.8
239 | 233 | IL | Kane | 60T10 | US-20 Intersection Improvements (CMAQ $$) | 3.3 | 2014-05-06 | 2014-08-12 | 2014-08-22 | 2014-08-26 | 5.5
240 | 234 | IL | Cook | 60W28 | FAI 90/94/290 Interchange reconstruction | 46 | 2014-05-06 | 2014-07-01 | 2014-07-11 | 2014-08-15 | 55.8
241 | 235 | IL | McHenry | 60W91 | US-14 | 2.835 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 2.5
242 | 236 | IL | Will | 60X60 | I-55 rehab - Blodgett Rd at Grant Creek | 2 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 1.8
243 | 237 | IL | Rock Island | 64G65 | I-88 Resurfacing | 14.5 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 15.6
244 | 238 | IL | Carroll | 64J31 | Resurfacing | 2.25 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 2.2
245 | 239 | IL | Rock Island | 64J68 | Reconst 3rd Ave - 19th St to 23rd St in Moline | 7.297 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-31 | 6.9
246 | 240 | IL | LaSalle | 66A35 | Resurfacing I-80 | 8.27 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 8.5
247 | 241 | IL | Kendall | 66D39 | IL-126 Safety Improvements | 2.1 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-08-25 | 1.4
248 | 242 | IL | McLean | 70A28 | I-39 Reconstruction | 11.34 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 12.8
249 | 243 | IL | Marion | 76F28 | US-50 Resurf & Guardrail - 6.44 miles | 3.3 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 3.1
250 | 244 | IL | Madison | 76G58 | IL-140 resurfacing - 6.64 miles | 2 | 2014-05-06 | 2014-05-09 | 2014-06-13 | 2014-07-25 | 3.1
251 | 245 | CT | New Haven | 151-273 | I-84 Reconstruct 2.7 miles in Waterbury | 448 | 2014-05-28 | 2014-06-25
252 | 246 | IL | Coles | 74423 | IL-16/Harrison Ave Turnlanes & Resurfacing | 3 | 2014-06-18 | 2014-07-01 | 2014-08-01 | 2015-01-17 | 2.6
253 | 247 | IL | Saline & Pope | 78430 | IL-34 Resurfacing | 2.4 | 2014-06-18 | [5 empty] | Withdrawn
254 | 247 | IL | Kane | 60N38 | IL-38 reconstruction | 4.43 | 2014-06-18 | 2014-07-03 | 2014-08-01 | 2014-08-25 | 4.7
255 | 248 | IL | Boone | 64H90 | 14 mile resurfacing IL-76 WI SL to US-20 Bus | 4.2 | 2014-06-18 | 2014-07-03 | 2014-08-01 | 2014-09-18 | 3.9
256 | 249 | IL | Madison | 76G24 | IL-203 resurfacing 3.3 miles | 4.4 | 2014-06-18 | 2014-07-03 | 2014-08-01 | 2014-08-26 | 1.3
257 | 250 | CA | LosAngeles & Orange | 123545 | 6th St Viaduct/Bridge Replacement (City of LA) | 419 | 2014-06-24
258 | 251 | NY | Monroe | 4940T7 | Reconstruct Segment of Rochester Inner Loop Express into a modern day "complete street" | 23.6 | 2014-06-27
259 | 252 | IL | Randolph | 76409 | Root Rd over Kaskaskia River Bridge Rehab | 2.7 | 2014-08-05 | 2014-08-15 | 2014-09-19 | 2014-10-24 | 2.4
260 | 253 | IL | Alexander | 78400 | US-60/62 | 3 | 2014-08-05 |  | 2014-09-19 | 2014-10-22 | 2.8
261 | 254 | IL | Cook | 60J16 | IL Rte 171 SB - Bridge Rehab | 38.615 | 2014-08-05 | 2014-08-15 | 2014-09-19 | 2014-10-24 | 26.2
262 | 255 | IL | Will | 60L71 | US-6/IL-7 Widening reconstr Gougar Rd to Will Rd | 55.7 | 2014-08-05 | 2014-12-18 | 2015-01-30 | 2015-04-03 | 57.1
263 | 256 | IL | Cook | 60L72 | US-6/IL-7 Widening Will Rd to Ravinia Ave | 48.5 | 2014-08-05 | 2014-12-18 | 2015-01-30 | 2015-03-12 | 47.2
264 | 257 | IL | Kane | 60T27 | US20 roadway improvements | 5.7 | 2014-08-05 |  | 2014-12-19 | 2015-03-19 | 5.2
265 | 258 | IL | Cook | 60W77 | IL 171 over I-55 Bridge Replacement | 7.843 | 2014-08-05 | 2014-08-15 | 2014-09-19 | 2014-10-24 | 8.8
266 | 259 | IL | Lake | 60X23 | IL21 Church to Townline - Road improvements | 2.8 | 2014-08-05 | 2014-08-15 | 2014-09-19 | 2014-10-22 | 4.3 |  | STA funded
267 | 259 | IL | Madison | 76F13 | I-70 reconstruct 9.14 miles | 25 | 2014-08-05 | 2014-08-15 | 2014-09-19 | 2014-10-24 | 29.9
268 | 260 | IL | Clinton | 76G31 | IL161 Resurfaceing 15 miles | 6.1 | 2014-08-05 | 2014-08-15 | 2014-09-19 | 2014-11-05 | 3.7
269 | 261 | IL | St Clair | 76G55 | IL159 Resurfacing & Guardrail improvments | 3.6 | 2014-08-05 | 2014-08-15 |  |  |  |  | STA funded
270 | 261 | NY | Kings & Queens | D900011 | BQE/I-278 Replacement of Kosciuszko Bridge over Newton Creek (D-B) | 550 | 2014-08-05 |  | 2013-12-04 | 2014-05-23 | 554.77
271 | 262 | CA | Contra Costa | 0662-6R4025 | Marsh Creek Safety Improvements | 1.2 | 2014-09-16
272 | 263 | MA | Hampden | 607731 | I-91 Viaduct rehab over East & West Columbus Ave in Springfield | 230 | 2014-09-23
273 | 264 | MN | St Louis | SP-069-609-038 | Martin Rd pavement rehab | 3.1 | 2014-09-23
274 | 265 | NY | Westchester | 8760.92 | Ashford Ave Bridge Rehab | 20 | 2014-10-02
275 | 266 | CA | Contra Costa | STPL_5928(120) | Countywide overlays - Pleasant Hill Rd, Byron Hwy, & Vasco Rd | 2.5 | 2014-10-02
276 | 267 | IL | Marshall | 68580 | IL-89 | 5.6 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 6.1
277 | 268 | IL | Lawrence | 74246 | IL-250 bridge replacement | 3.74 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2015-01-07 | 2.8
278 | 269 | IL | Coles | 74350 | IL-133 pavement rehab | 4.09 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 3.1
279 | 270 | IL | Moultrie | 74357 | IL-32 bridge rehab | 5.8 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 2.7
280 | 271 | IL | Macon | 74624 | IL-121/48 pavement rehab | 4.84 | 2014-10-14 |  | 2014-11-21 | 2015-04-07 | 5.7
281 | 272 | IL | Jersey | 76789 | IL-3 pavement rehab | 10.6 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2015-02-11 | 13.7
282 | 273 | IL | Williamson | 78380 | I-57 | 21.1 | 2014-10-14 |  | 2014-11-21 |  |  |  | Status Unknown
283 | 274 | IL | Jefferson | 78437 | I-57 | 7.8 | 2014-10-14 |  | 2014-11-21 |  |  |  | Status Unknown
284 | 275 | IL | Will | 60P95 | US-30 widen/reconstr IL-59 toI-55 | 25.8 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2015-03-09 | 21
285 | 276 | IL | Kane | 60X70 | US-30 @ Dugan Rd intersection reconstr | 7.8 | 2014-10-14 |  | 2014-12-19 | 2015-03-26 | 8.5
286 | 277 | IL | Will | 60X84 | I-55 inchange ramp constr | 10.5 | 2014-10-14 |  | 2014-12-19 | 2015-03-23 | 8.9
287 | 278 | IL | Whiteside | 64C17 | IL-40 bridge replacemnt @ Hennepin Canal Feeder | 3.3 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 5.2
288 | 279 | IL | Henry | 64G63 | I-80 pavement rehab | 10 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 8.6
289 | 280 | IL | Henry | 64G64 | I-80 pavement rehab | 21 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 18.2
290 | 281 | IL | Henry | 64J43 | US-6/IL-84 intersection reconstr | 3.6 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 5
291 | 282 | IL | Grundy | 66B27 | I-80 | 2.8 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 3.1
292 | 283 | IL | Kendall | 66B84 | IL-47 | 62 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2015-01-17 | 46.2
293 | 284 | IL | Grundy | 66B91 | US-67 bridge reconstruction | 3.4 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 2.6
294 | 285 | IL | Knox | 68B85 | I-74 | 5.5 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 3
295 | 286 | IL | McLean | 70A20 | I-39 | 6.12 | 2014-10-14 |  | 2014-11-21 |  |  |  | Status Unknown
296 | 287 | IL | Sangamon | 72B54 | I-72 | 20 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 21.6
297 | 288 | IL | Morgan/Pike | 72B58 | IL-104/US-67 | 61.9 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2015-03-12 | 75.1
298 | 289 | IL | Sangamon | 72G47 | I-55 | 4.6 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 5.5
299 | 290 | IL | St. Clair | 76B03 | Illinois Ave bridge rehab | 15 | 2014-10-14 | 2014-10-17 | 2014-11-21 | 2014-12-30 | 15.9
300 | 291 | IL | St. Clair | 76G09 | I-64 pavement rehab | 27 | 2014-10-14 |  | 2015-01-30 |  |  |  | Status Unknown
301 | 292 | MN | St Louis | SP-069-609-013 | Arlington Ave pavement rehab | 2 | 2014-10-27
302 | 293 | IL | Iroquois | 66736 | IL-1 Bridge remove/replace | 3.7 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-04 | 4.8
303 | 294 | IL | Macon | 74515 | IL48/Wyckles Rd reconstr | 2.1 | 2014-12-02 |  | 2015-01-16 |  |  |  | Status Unknown
304 | 295 | IL | Peoria | 89657 | Nebraska St Bridge | 0.8 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-12 | 0.9
305 | 296 | IL | Lake | 60K99 | US41 resurfacing | 8 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-12 | 11.6
306 | 297 | IL | Cook | 60W30 | I90/94/290 Taylor St Bridge Rehab | 14.2 | 2014-12-02 |  | 2015-01-16 | 2015-04-03 | 17.7
307 | 298 | IL | Cook | 60X61 | I90/94/290 WB resurfacing | 9.5 | 2014-12-02 |  | 2015-01-16 | 2015-04-16 | 20.5
308 | 299 | IL | Cook | 60Y26 | US6/179 St realignment | 2.5 | 2014-12-02 | 2015-01-30 | 2015-03-06 |  |  |  | Status Unknown
309 | 300 | IL | DuPage | 60Y95 | IL390/I290 interchange reconstr | 43 | 2014-12-02 |  | 2015-01-16 | 2015-04-23 | 36.5
310 | 301 | IL | Henry | 64C05 | I74/I80 resurfacing | 14.6 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-04 | 16.6
311 | 302 | IL | Ogle & Winnebago | 64G62 | I39 resurfacing | 30 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-04 | 33
312 | 303 | IL | Morgan | 72A97 | IL-78 bridge replace; resurfacing | 3.8 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-04 | 3.3
313 | 304 | IL | Hancock | 72C60 | IL9/IL94 pavement reconstruction | 3.4 | 2014-12-02 | 2014-12-18 | 2015-01-30 |  |  |  | Status Unknown
314 | 305 | IL | Sangamon | 72F49 | I-55 bridge deck replacement | 4.2 | 2014-12-02 | 2014-12-18 | 2015-01-30 | 2015-03-04 | 4
315 | 306 | IL | Kankakee | 66982 | I-57 Pavement Rehab | 51 | 2015-01-16 |  | 2015-03-06 |  |  |  | Status Unknown
316 | 307 | IL | Vermillion | 70788 | IL49(N) to US150 resurfacing | 12.7 | 2015-01-16 | 2015-01-30 | 2015-03-06 | 2015-04-15 | 13.1
317 | 308 | IL | Champaign | 70844 | IL47 resurfacing | 7 | 2015-01-16 |  | 2015-03-06 | 2015-04-15 | 8.2
318 | 309 | IL | Pike | 72840 | IL100 R&R 3 bridges | 2.3 | 2015-01-16 |  | 2015-03-06 | 2015-04-02 | 1.4
319 | 310 | IL | Union & Johnson | 78286 | I57 reconstruction | 31.7 | 2015-01-16 |  | 2015-03-06 | 2015-04-16 | 30
320 | 311 | IL | Union & Pulaski | 78319 | I57(SB) reconstr resurface | 7.9 | 2015-01-16 |  | 2015-03-06 | 2015-04-15 | 8.1
321 | 312 | IL | "multicounty D9" | 78396 | Guardrail, shoulder improvements | 2.2 | 2015-01-16 |  | 2015-03-06 | 2015-04-03 | 0.3
322 | 313 | IL | DuPage | 60W55 | IL83/63 St culvert replacement | 3.6 | 2015-01-16 |  | 2015-03-06 | 2015-04-23 | 4.3
323 | 314 | IL | Lake | 60W99 | US41 safety improvements | 2.7 | 2015-01-16 | 2015-01-30 | 2015-03-06 |  |  |  | Status Unknown
324 | 315 | IL | Cook | 60X56 | I-90 flyover bridge project | 36.7 | 2015-01-16 | 2015-01-30 | 2015-03-06 |  |  |  | Status Unknown
325 | 316 | IL | Champaign | 70A54 | IL130 resurfacing | 3 | 2015-01-16 |  | 2015-03-06 | 2015-04-03 | 2.9
326 | 317 | IL | Sangamon | 72G92 | I72 pavement rehab | 11 | 2015-01-16 |  | 2015-03-06 | 2015-03-27 | 8.8
327 | 318 | IL | Jackson | 78056 | Replace IL-3 bridges over Big Muddy River | 13 |  | 2012-03-23 | 2012-04-27 | 2012-05-17 | 11.9
| 319 | MN | St Louis | 069-604-073 | CSAH 24 to Rice Lake Rd - Sidewalk construction | 0.4 | 2015-09-18
| 320 | MN | St Louis | 069-609-040 | CSAH 9 - Resurfacing; utility improvements; add bike lanes | 9.5 | 2015-09-18
| 321 | MN | St Louis | 069-623-032 | CSAH 23 to Buyck Rd - 16 miles pvmt preservation | 4.75 | 2015-09-18
| 322 | DC | Washington |  | South Capital Street Corridor Project - Phase I | 608 | 2016-02-09
| 323 | CA | Contra Costa | HRRRL-5928(117) | Byron Hwy/Camino Diablo Intersec Improve | 2.3 | 2016-05-06
| 324 | PA | Montgomery | 80021 | SR202/Sect 510 Markley St Reconstruction | 25 | 2017-01-09
| 325 | NY | Bronx | X72699 | Bridge Deck (3) Rehab - along Cross Bronx Epwy High-BR Interchange | 45.5 | 2017-03-30
| 326 | NY | Orange | 800684 | Reconstr NYS Rt 17 @ 32, Exit 131 | 108 | 2017-07-28
| 326 | NY | Bronx, Queens, & Kings | X80723 | Bridge Deck (3) Rehab - NYC | 35 | 2017-03-30
| 327 | NY | Bronx | X73147 | Bridge Decks (5) Rehab - Staten Island & Brooklyn | 58.5 | 2017-11-07
| 327 | NY | Bronx | X73145 | Bridge Deck (6) Rehab - Bruckner Viaduct NYC | 163 | 2017-03-30
| 328 | CT | Litchfield | 151-312, 151-313, and 515-326 | I-84/Rte 8 Interchange Bridge (10) Reconstr | 180 | 2017-11-21
| 331 | CA | Contra Costa | BRLS-5928(107) | Marsh Creek Road Bridge Replacement | 5 | 2017-12-15
328 | 331 | IL | Cook | "various" | City of Chicago "Multi-PLA" on projects >$25,000 |  |  |  | 2011-01-13 |  |  |  | Withdrawn
| 332 | NY | Nassau | PIN D900042/ PIN 0072.14 | Nassau expressway Operational & Resiliency Improvements Project. | 100 | 2018-02-20
| 333 | MN | St. Louis | SP 088-070-050; SP069-090-018; SP 069-644-030 | 3 projects (dynamic warning system; and two roadway reconstruction projects | 3.49 | 2018-03-07
| 334 | CT | New London | Proj No. 94-256 | Superstructure strengthening, Gold Star Bridge (I-95 over Thames River) | 100 | 2018-05-01
| 335 | NY | Queens | PIN X051.60 | Kew Gardens Interchange | 340 | 2018-05-15
| 336 | CA | Contra Costa | STPL-5928(123) | Kirker Pass Road NB Truck Climbing Lane | 14.3 | 2018-06-05
| 337 | CA | Contra Costa | HSIPL-5928(131) | Byron Highway Traffic Safety Improvements | 0.5 | 2018-11-28
| 338 | CA | Contra Costa | HSIPL-5928(130) | Marsh Creek Road Highway Traffic Safety Improvements | 1.002 | 2018-11-28
| 339 | CA | Contra Costa | STPL-5928 (148) | Local Streets and Roads Preservation Project | 3.844 | 2018-11-28
| 340 | MN | St. Louis | SP 069-070-038 | J-Turn Intersection CSAH 7 (Hwy 7)/CR 885 (Industrial Road) | 0.9 | 2018-11-28
| 341 | MN | St. Louis | SP 069-598-065, SP 069-606-025, SP 069-700-015 | 3 projects (one county bridge and two full depth pavement reclamation projects) | 6.4 | 2018-12-17
| 342 | NY | Bronx | PIN X72039 | Rehabilitation of the Major Deegan Expressway | 166.8 | 2019-02-26
| 343 | CA | Contra Costa | ATPL-5928(136) | Bailey Road/SR 4 Interchange and Ped-Bike Improvements | 5.3 | 2019-03-29
| 344 | NY | Bronx | PIN X731.63 (D900047) | Hunts Point Interstate Access Improvement | 597.5 | 2019-04-30
1 | 345 | NY | Putnam | PIN 8127.26 | Taconic State Parkway at Pudding Street Grade Separation | 26.1 | 2019-05-23
| 346 | CA | Contra Costa | HSIPL-5928(145) | Countywide Guardrail Upgrade | 1.65 | 2019-06-01
| 347 | CA | Los Angeles & Orange | LA0G1448 (STIP) | Double Track Access from Pier G to Pier J | 17.043 | 2019-07-11
| 348 | CA | LosAngeles & Orange | Spec 2784 & Spec 2805 | Port of LA Alameda Corridor Southern Terminus Gap Closure & Pier 400 Corridor Storage Tracks Expansion | 43.5 | 2019-08-21
| 349 | NY | Westchester | PIN 8101.46 (D900049) | Lower Westchester Bridge Bundle (5 structures) | 100 | 2019-09-25
| 350 | IL | Peoria, Tazewell | 68C89 | I-74/IL 29 — Murray Baker Bridge rehabilitation | 35 | 2019-10-03
| 351 | IL | Cook | 62J31 | I-90/I94 at I-290 reconstruction | 9.65 | 2019-10-03
| 352 | IL | Cook | 62F95 | I-94 at Montrose Avenue overpass rehabilitation | 12.5 | 2019-10-03
| 353 | IL | Champaign | 70B98 | I-57 under US 150 overpass reconstruction | 7.2 | 2019-10-03
| 354 | IL | Champaign | 70B38 | Mattis Avenue over I-57 and I-74 structure reconstruction | 18.9 | 2019-10-03
| 355 | IL | St. Clair | 76E13 | I-255 resurfacing and structure rehabilitation | 72 | 2019-10-03
| 356 | IL | Grundy | 66A51 | I-55 resurfacing | 22 | 2019-10-03
| 357 | NY | Suffolk | PIN 0017.67.121 | Robert Moses Causeway over Fire Island Inlet Bridge rehabilitation | 26.32 | 2019-11-05
| 358 | IL | Champaign | 70C64 | I-74 structure rehabiltation (over ICRR & Market St) | 26.4 | 2019-11-21
| 359 | IL | McLean | 70912 | I-55 pavement resurfacing and rehabilitation | 14.6 | 2019-11-21
| 360 | IL | LaSalle | 66H21 | I-80 structure rehabilitation, LaSalle Road to Little Vermillion River | 15.1 | 2019-11-21
| 361 | IL | Bureau & Putnam | 66F08 | I-180 deck replacement over Illinois River | 34 | 2019-11-21
| 362 | IL | Adams | 72A91 | IL-57 rehabilitation | 7.2 | 2019-11-21
| 363 | IL | Logan | 72G57 | I-55 & I-55 Bus. Rehabilitation | 21.8 | 2019-11-21
| 364 | IL | Winnebago | 64L72 | I-39, US-20 & Baxter Road pavement rehabilitation | 21 | 2019-11-21
| 365 | IL | Winnebago | 64L57 | IL-251 resurfacing | 14.6 | 2019-11-21
| 366 | IL | Coles | 74260 | IL-121 pavement rehabilitation | 6.88 | 2019-11-21
| 367 | IL | Woodford | 68E34 | I-39 resurfacing | 8 | 2019-11-21
| 368 | IL | Coles | 74694 | IL-76 pavement rehabilitation | 5.32 | 2019-11-21
| 369 | NY | Ulster | PIN 801846/ D264093 | Route 28 over Esopus Creek structure replacement | 25 | 2019-12-20
| 370 | MN | St Louis | SP 069-607-052 | CSAH-7 pavement rehabilitation | 5.5 | 2019-12-31
| 371 | IL | Peoria | 68C98 | IL-6 ramp resurfacing | 13 | 2020-01-28
| 372 | IL | Woodford | 68E24 | I-39 resurfacing | 10.5 | 2020-01-28
| 373 | IL | Montgomery | 72D31 | I-55 resurfacing & structure rehabilitation | 23.98 | 2020-01-28
| 374 | IL | Lawrence | 74411 | IL-1 pavement rehabilitation | 6.29 | 2020-01-28
| 375 | CA | Los Angeles & Orange | HD-S3009 | Coastal Bike Trail Connector at Ocean Boulevard | 16 | 2020-03-24
| 376 | IL | Cook | 62A76 | I-90/I-94 Northbound Reconstruction | 47.91 | 2020-03-13
| 377 | IL | Cook | 62A77 | I-90/I-94 Southbound Reconstruction | 47.95 | 2020-03-13
| 378 | IL | Rock Island | 64J28 | IL-5 resurfacing | 5 | 2020-03-13
| 379 | IL | Boone & Winnebago | 64N36 | US 20 dowel bar retrofit | 7 | 2020-03-13
| 380 | IL | Peoria | 68A81 | IL-29 resurfacing | 9.6 | 2020-03-13
| 381 | IL | Logan | 72E23 | I-155 resurfacing | 7.5 | 2020-03-13
| 382 | IL | Sangamon | 72G46 | I-55 resurfacing | 19.68 | 2020-03-13
| 383 | IL | Christian | 72G70 | IL-29 resurfacing | 7.1 | 2020-03-13
| 384 | IL | Sangamon | 72H51 | I-72 bridge deck replacement | 7.5 | 2020-03-13
| 385 | IL | Cumberland | 74542 | US 40 pavement rehabilitation | 5.51 | 2020-03-13
| 386 | IL | Macon | 74779 | US 51 pavement rehabilitation | 13.96 | 2020-03-13
| 387 | IL | Effingham | 74907 | US 45 pavement rehabilitation | 5.68 | 2020-03-13
| 388 | IL | Macon | 74917 | Old Route 36 pavement rehabilitation | 7.79 | 2020-03-13
| 389 | MN | St. Louis | SP-069-060-002 | CSAH-61 French River Wayside Rest Area Reconstruction | 1.1 | 2020-03-31
| 390 | MN | St. Louis | SP-069-090-033 | Mesabi Trail - TH 169 Underpass to CSAH 88 | 0.9 | 2020-03-31
| 391 | MN | St. Louis | SP-069-643-017 | CSAH 43 pavement rehabilitation | 3.1 | 2020-03-31
| 392 | IL | Randolph | 76J71 | IL-3 Resurfacing, ADA & storm sewer improvements | 7.8 | 2020-05-01
| 393 | NY | Otsego & Schoharie | PIN 93588.22 | I-88 Resurfacing & Bridge Rehabilitation | 43.2 | 2020-04-17
| 394 | NY | Ulster | PIN 8808.62/ D264169 | Wurts Street bridge rehabilitation | 38.7 | 2020-04-20
| 395 | IL | Jersey | 76568 | US 67 expressway construction | 24 | 2020-06-09
| 396 | IL | Vermillion | 70A92 | I-74 superstructure replacement | 17.8 | 2020-06-09
| 397 | IL | Jefferson | 78600 | I-57 resurfacing | 7.6 | 2020-06-09
| 398 | IL | Williamson | 78787 | I-57 resurfacing | 9 | 2020-06-09
| 399 | IL | Peoria | 68F15 | I-74 resurfacing | 15 | 2020-06-25
| 400 | IL | Macon | 74710 | 19th Street pavement rehabilitation | 5.7 | 2020-06-25
| 401 | IL | Henderson | 68F21 | IL-64 resurfacing | 5.8 | 2020-06-25
| 402 | NY | Queens | PIN X735.80 D264076 | Van Wyck Expressway Viaduct Deck Replacement | 144 | 2020-07-27
| 403 | IL | Cook | 60P14 | IL-72 & IL-83 Intersection Improvements | 5.14 | 2020-08-11
| 404 | IL | Lake | 62B65 | New pump station | 11.8 | 2020-08-11
| 405 | IL | Winnebago | 64L14 | US 20 intersection improvements | 6.2 | 2020-08-11
| 406 | IL | Madison | 76H84 | I-70, I-270, I-55/70 resurfacing | 21 | 2020-08-11
| 407 | IL | Greene & Jersey | 76L20 | US 67 resurfacing | 4.4 | 2020-08-11
| 408 | IL | Will | 60W34 | I-80 eastbound resurfacing/widening | 41.2 | 2020-09-17
| 409 | IL | McHenry | 62A80 | IL-47 at Kishwaukee River structure replacement | 7.1 | 2020-09-17
| 410 | IL | Will | 62M63 | I-55 at IL-59 interchange reconstruction | 11 | 2020-09-17
| 411 | IL | Rock Island | 64F78 | I-280 resurfacing and deck replacement | 40 | 2020-09-17
| 412 | IL | Ford | 66K20 | IL-9 resurfacing | 6.6 | 2020-09-17
| 413 | IL | Warren | 68D95 | US 34 structure replacement | 5.2 | 2020-09-17
| 414 | IL | McLean | 70A65 | Veterans Parkway (FAP 704) resurfacing | 6.5 | 2020-09-17
| 415 | IL | Adams | 72L58 | US 24 Memorial Bridge rehabilitation | 12 | 2020-09-17
| 416 | IL | St. Clair | 76B55 | I-70 structure rehabilitation | 35.4 | 2020-09-17
| 417 | IL | Wayne | 74982 | I-64 pavement rehabilitation | 7.3 | 2020-09-17
| 418 | IL | Franklin | 78481 | IL-149 pavement reconstruction & resurfacing | 3.8 | 2020-09-17
| 419 | IL | Pulaski | 78785 | Old US 51 (FAS 2936) resurfacing | 9 | 2020-09-17
| 420 | IL | Vermillion | 90922 | Tilton Road over I-74 structure replacement | 4.5 | 2020-09-17
| 421 | CA | Los Angeles & Orange | HD-S2556 | Gerald Desmond Bridge Demolition | 44.2 | 2020-10-02
| 422 | MN | St. Louis County | SP 069-605-049 | CSAH 5 pavement rehabilitation & resurfacing | 1.44 | 2020-11-04
| 423 | MN | St. Louis County | SP 069-629-007 | CSAH 29 pavement rehabilitation & resurfacing | 3.4 | 2020-11-04
| 424 | MN | St. Louis County | SP 069-656-018 | CSAH 56 pavement rehabilitation & resurfacing | 2.65 | 2020-11-04
| 425 | MN | St. Louis County | SP 069-665-008 | CSAH 65 bridge replacement | 1.2 | 2020-11-04
| 426 | MN | St. Louis County | SP 069-716-012 | CSAH 116 resurfacing | 1.44 | 2020-11-04
| 427 | IL | Will | 62M06 | I-55 resurfacing | 12.4 | 2020-11-18
| 428 | IL | Winnebago | 64H08 | US 20 BUS (W. State St.) roadway reconstruction | 8 | 2020-11-18
| 429 | IL | Madison | 76M48 | Resurfacing on IL 157 | 4.8 | 2020-11-18
| 430 | IL | Madison | 76M84 | Resurfacing on IL 159 | 8.5 | 2020-11-18
| 431 | IL | Shelby & Macon | 74549 | Rehabilitation on US 51 | 7.1 | 2020-11-18
| 432 | IL | Macon | 74757 | I-72 reconstruction | 28.7 | 2020-11-18
| 433 | IL | Massac | 78606 | I-24 bridge repair and resurfacing | 22.9 | 2020-11-18
| 434 | NY | Westchester | PIN 8813.68 / D264324 | Westchester County Bridge Rehabilitation (4 bridges) | 27.8 | 2020-11-17
| 435 | CA | Contra Costa | ATPL 5928(151) | Fred Jackson 1st/Last mile complete streets construction | 2.9 | 2020-12-18
| 436 | CA | Contra Costa | BRLS-5928(128) | Marsh Drive bridge over Walnut Creek replacement | 14.6 | 2020-12-18
| 437 | NV | Clark |  | I-15 Tropicana Avenue Interchange Reconstruction | 200 | 2020-12-22
#REF! | ** Information sorted by Approved date
| 437 |  |  |  |  | 12014.65

## Table B - Chicago
ID # | # | State Contract # | Description | Cost (M) est. | Approved** | Advertise | Letting | Award | Award Cost (M) | Column3 | Omisison Reason
1 |  | 66908 | Resurface 7.5 miles of I-80 | 30.4 | 2009-10-16 | 2009-10-02 | 2009-11-06 | 2009-12-21 | 22.2 |  | Pre-May 7, 2010 guidance
2 |  | 76323 | Reconstruct 3.5 miles IL-255 new alignment | 22 | 2010-01-27 | 2010-01-29 | 2010-03-05 | 2010-04-22 | 21.9 |  | Pre-May 7, 2010 guidance
3 |  | 76830 | Widen and resurface IL-159 | 8.9 | 2010-02-03 | 2010-05-07 | 2010-06-11 | 2010-07-20 | 9.4 |  | Pre-May 7, 2010 guidance
4 |  | 76D61 | Construct I-70 Mississippi River Bridge | 60 | 2010-03-17 | 2010-04-09 | 2010-05-14 | 2010-06-25 | 46.3 |  | Pre-May 7, 2010 guidance
5 |  | D261390 | Construct 5 bridges on I-287 @ Exit 8 | 54 | 2010-03-25 |  | 2010-03-31 | 2010-07-21 | 53 |  | Pre-May 7, 2010 guidance
|  | 76311 | Construct 3.2 miles of US-67/IL-267 | 23 | 2010-05-06 | 2010-05-07 | 2010-06-11 | 2010-08-20 | 21.4 |  | Pre-May 7, 2010 guidance
|  | 76318 | Construct 2.0 miles of US-67 | 27 | 2010-05-06 | 2010-06-25 | 2010-07-30 | 2010-10-01 | 20.4 |  | Pre-May 7, 2010 guidance
1 | 1 | C-88-009-11 | Madison Street Viaduct over Chicago Union Station Tracks |  | 2011-01-25 |  |  | 2011-06-02 | 6.8
2 | 2 | C-88-011-10 | Arterial Resurfacing #58 (FAR SOUTH) |  | 2010-09-07 |  |  | 2011-06-30 | 7.8
3 | 3 | C-88-010-10 | Arterial Resurfacing #57 (SOUTH) |  | 2010-09-07 |  |  | 2011-06-30 | 7.4
4 | 4 | C-88-012-10 | Torrence Ave vertical lift bridge rehab |  | 2010-11-19 |  |  | 2011-06-30 | 24.1
5 | 5 | C-88-008-10 | Arterial Resurfacing #55 (NORTH) |  | 2010-09-07 |  |  | 2011-07-05 | 5.3
6 | 6 | C-88-009-10 | Arterial Resurfacing #56 (CENTRAL) |  | 2010-09-07 |  |  | 2011-07-05 | 9.2
#REF! | 7 | C-88-010-09 | Bridge Painting - 2009 (Contract B) |  | 2010-09-07 |  |  | 2011-07-18 | 1.3
#REF! | 8 | C-88-009-09 | Bridge Painting - 2009 (Contract A) |  | 2010-09-10 |  |  | 2011-07-22 | 0.8
#REF! | 9 | C-88-038-10 | Arterial Street ADA Ramps - 2010 (South) |  | 2010-12-16 |  |  | 2011-08-26 | 2.8
#REF! | 10 | C-88-039-10 | Arterial Street ADA Ramps - 2010 (Central) |  | 2010-12-16 |  |  | 2011-08-26 | 2.8
#REF! | 11 | C-88-002-11 | City Wide Miscellaneous Viaduct Improvements - TIGER |  | 2010-10-15 |  |  | 2011-09-08 | 4.1
#REF! | 12 | C-88-023-10 | Wacker Drive: Monroe Street to Van Buren Street | 122 | 2011-09-16 |  |  | 2011-12-22 | 83.3
#REF! | 13 | C-88-016-07 | Undertake access improvements to US Rt41, Chicago | 33.4 | 2011-09-21 |  |  | 2012-01-06 | 18.9
#REF! | 14 | C-88-022-11 | Kedzie Ave Bridges over Marquette Park Lagoons | 6.5 | 2011-09-21 |  |  | 2012-02-08 | 6.2
#REF! | 15 | C-88-020-02 | Replacement of Fullerton Ave bridge and pedestrian walkway | 15.5 | 2011-09-07 |  |  | 2012-02-10 | 11.6
#REF! | 16 | C-88-008-12 | Bike Sharing Program | 22.5 | 2011-11-29 |  |  | 2012-05-07 | 65
#REF! | 17 | C-88-019-11 | Various Arterial Streets ADA Ramps - 2011 (Central) | 3.3 | 2012-01-19 |  |  | 2012-06-25 | 2.4
#REF! | 18 | C-88-015-12 | Aerial Street Resurfacing Project Number 59-North Area | 12.7 | 2012-05-18 |  |  | 2012-08-08 | 11.4
#REF! | 19 | C-88-017-12 | Arterial Street Resurfacing Project Number 61-South Area | 14.5 | 2012-05-18 |  |  | 2012-08-08 | 12.7
#REF! | 20 | C-88-016-12 | Arterial Street Resurfacing Project Number 60-Central Area | 14.5 | 2012-05-18 |  |  | 2012-08-20 | 12.7
#REF! | 21 | C-88-018-11 | Various Arterial Streets ADA Ramps - 2011 (North) | 2.1 | 2012-01-19 |  |  | 2012-08-22 | 1.6
#REF! | 22 | C-88-018-12 | Arterial Street Resurfacing Project Number 62-Far South Area | 13.3 | 2012-05-18 |  |  | 2012-09-25 | 12.5
#REF! | 23 | C-88-041-12 | For the improvement of the Wells Street Bridge over the Main Branch of the Chicago River | 47.5 | 2012-06-19 |  |  | 2012-10-17 | 41.2
#REF! | 24 | C-88-001-12 | Painting of bridges & viaducts at various locations throughout City of Chicago (Project # 1) | 1.9 | 2012-01-19 |  |  | 2012-11-28 | 1.7
#REF! | 25 | C-88-002-12 | Painting of bridges and viaducts at various locations throughout the City of Chicago (Project # 2) | 1.6 | 2012-01-19 |  |  | 2012-11-28 | 1.4
#REF! | 26 | C-88-014-11 | Chicago Greenstreets Tree Planting Project at Various Westside Area Locations | 0.5 | 2012-01-19 |  |  | 2013-01-28 | 0.4
#REF! | 27 | C-88-003-12 | Michigan Ave vaulted sidewalk ADA Ramps-2011: Lake Street to Van Buren Street | 1.9 | 2012-05-04 |  |  | 2013-03-28 | 1.6
#REF! | 28 | C-88-047-06 | 57th Street @ Lake Shore Drive: Traffic Mitigation & Circulation Enhancement. | 3 | 2012-12-06 |  |  | 2013-04-25 | 2
#REF! | 29 | C-88-035-06 | Foster Ave at Kedzie Ave Streetscape; Foster Ave from Albany Ave to Kimball Ave | 4.6 | 2012-07-05 |  |  | 2013-05-02 | 2.9
#REF! | 30 | C-88-005-11 | Milwaukee Ave Reconstruction Project - Kilpatrick Ave to Addison Street | 9.6 | 2012-11-29 |  |  | 2013-05-08 | 6.6
#REF! | 31 | C-88-004-12 | Vaulted sidewalk ADA Ramp Program State Street corridor (Haddock Place to Jackson Street) | 1.6 | 2012-06-25 |  |  | 2013-05-15 | 1.7
#REF! | 32 | C-88-023-11 | Various traffic signal modernization - 2009 | 5.3 | 2012-08-08 |  |  | 2013-07-18 | 4.1
#REF! | 33 | C-88-008-08 | Traffic Control signals @ various locations throughout the City of Chicago - 2008 Program | 4.4 | 2012-08-16 |  |  | 2013-07-30 | 3
#REF! | 34 | C-88-017-13 | The improvement of Bloomingdale Trail, Ridgeway Av. to the Kennedy Expressway | 61 | 2013-04-25 |  |  | 2013-08-20 | 53.8
#REF! | 35 | C-88-043-12 | Viaduct removal at Ashland Av4 over Pershing Road | 12.5 | 2012-12-11 |  |  | 2013-10-10 | 11.4
#REF! | 36 | C-88-012-13 | Streets for Cycling, Project # 2 includes upgrading existing bicycle paths to attract new users and improve safety | 2.5 | 2013-06-17 |  |  | 2013-10-25 | 1.4
#REF! | 37 | na | Chicago Riverwalk - Phase 2 from State Street to LaSalle Street | 42.3 | 2013-08-23 |  |  | 2013-11-07 | 43.1
#REF! | 38 | C-88-001-01 | Lakefront Bike Trail: Navy Pier Flyover consisting of new pedestrian bridge, furnishing structural steel, lighting, concrete | 26.4 | 2013-02-12 |  |  | 2013-12-05 | 22.5
#REF! | 39 | C-88-007-11 | Chicago Greenstreets Tree Planting-Mid South Area | 1 | 2011-06-22 |  |  | 2013-12-20 | 0.8
#REF! | 40 | C-88-020-07 | Gateway Green Kennedy Expressway landscaping enhancements. | 1 | 2013-02-07 |  |  | 2013-12-23 | 0.5
#REF! | 41 | C-88-022-12 | Arterial Street ADA Ramps Project #54 - Far South Area | 2.5 | 2013-02-01 |  |  | 2014-05-14 | 1.3
#REF! | 42 | C-88-019-12 | Arterial Street ADA Ramps Project #51 - North Area | 2.5 | 2013-02-01 |  |  | 2014-06-18 | 2.5
#REF! | 43 | C-88-021-12 | Arterial Street ADA Ramps Project #53 - South Area | 2.5 | 2013-02-01 |  |  | 2014-06-26 | 1.8
#REF! | 44 | C-88-020-12 | Arterial Street ADA Ramps Project #52 - Central Area | 2.5 | 2013-02-01 |  |  | 2014-06-30 | 4.3
#REF! | 45 | C-88-003-09 | 35th St over south Lake Shore Drive: bicycle & pedestrian bridge improvement | 22.3 | 2013-09-24 |  |  | 2014-07-10 | 18.3
#REF! | 46 | C-88-026-13 | Arterial Street Resurfacing Project #65 (South Area) | 12.8 | 2014-05-19 |  |  | 2014-07-24 | 7.2
#REF! | 47 | C-88-029-13 | Arterial Street Resurfacing Project # 66 (Far South Area) | 11.3 | 2014-05-19 |  |  | 2014-08-05 | 6.2
#REF! | 48 | C-88-025-13 | Arterial Street Resurfacing Project #63 (North Area) | 10.4 | 2014-05-19 |  |  | 2014-08-06 | 5.8
#REF! | 49 | C-88-028-13 | Arterial Street Resurfacing Project # 64 (Central Area) | 11.3 | 2014-05-19 |  |  | 2014-08-06 | 7.2
#REF! | 50 | C-88-022-13 | West Ridge Nature Preserve Pedestrian Trail, Chicago | 3.5 | 2014-02-21 |  |  | 2014-08-14 | 4.5
#REF! | 51 | C-88-015-10 | Various Pin and Link Expansion Joint Retrofits | 7 | 2014-03-11 |  |  | 2015-02-09 | 9.7459
#REF! | 52 | C-88-034-13 | Painting of bridges & viaducts @ various locations throughout the City of Chicago-Project #3 | 1.5 | 2014-05-28 |  |  | 2015-08-31 | 1.4791
#REF! | 53 | C-88-032-13 | Painting of bridges & viaducts @ various locations throughout the City of Chicago-Project #4 | 1.5 | 2014-05-28 |  |  | 2015-08-31 | 1.09
#REF! | 54 | C-88-041-13 | Fullerton Ave: Ashland to Racine Ave including removal/replacementof existing sidewalk & curb/gutter, ADA Ramps, HMA removal | 5.4 | 2014-07-11 |  |  | 2016-01-27 | 4.3243
#REF! | 55 | na | Chicago Riverwalk - Phase 3 from LaSalle Street to Lake Street | 42.6 | 2014-10-29 |  |  | 2015-05-29 | 52.4194
#REF! | 56 | C-88-026-06 | Construct underpass @ intersection of Damen/Fullerton/Elston Avenues Chicago - improvement of Damen, Elston & Fullerton Avenues | 16 | 2014-12-24 |  |  | 2015-05-08 | 16.9931
#REF! | 57 | C-88-001-14 | Streets for Cycling Project 2-Group B | 2.3 | 2015-02-12 |  |  | 2015-07-01 | 1.6596
#REF! | 58 | C-88-002-14 | For the improvement of the Adams Street Viaduct over Union Station | 35.9 | 2015-02-27 |  |  | 2015-11-23 | 33.812
| 59 | C-88-008-14 | Devon Avenue, California Avenue to Rockwell Street | 3.6875 | 2015-04-03 | 2016-02-04 | 1900-01-01 21:32 | 2016-02-04 | 2.8975
| 60 | C-88-018-14 | Arterial St. Resurfacing Project 69-South Area | 12.35 | 2015-06-02 | 2015-08-21 | 1900-01-07 18:59 | 2015-08-21 | 8.7909
| 61 | C-88-019-14 | Arterial Street Resurfacing Project 67-North Area | 10.55 | 2015-06-02 | 2015-08-21 | 1900-01-06 06:38 | 2015-08-21 | 7.2762
| 62 | C-88-020-14 | North Lake Shore Drive Rehabilitation, IL - Arterial St. Resurfacing Project 68-Central Area | 9 | 2015-06-02 | 2015-08-18 | 1900-01-06 16:23 | 2015-08-18 | 7.6829
| 63 | C-88-021-14 | Arterial St. Resurfacing Project 70-Far South Area | 8.1 | 2015-06-04 | 2015-08-18 | 1900-01-04 03:05 | 2015-08-18 | 5.1285
| 64 | C-88-003-15 | Western Avenue over Belmont Avenue | 36 | 2015-06-18 | 2015-12-16 | 1900-01-24 16:07 | 2015-12-16 | 25.6715
| 65 | C-88-001-16 | Ped bridge at 41st Street over Metra/IC RR and Lake Shore Drive | 29 | 2016-04-14
| 66 | C-88-009-15 | Arterial St. Resurfacing 71-North Area | 13.0446 | 2016-04-25 | 2016-07-27 | 1900-01-10 06:07 | 2016-07-27 | 11.2546
| 67 | C-88-010-15 | Arterial St. Resurfacing -South Area | 9.3297 | 2016-04-25 | 2016-07-27 | 1900-01-06 20:09 | 2016-07-27 | 7.8397
| 68 | C-88-012-15 | Arterial St. Resurfacing -Central Area | 8.184 | 2016-04-25 | 2016-07-27 | 1900-01-05 22:39
| 69 | C-88-013-15 | Arterial St. Resurfacing 74-Far South Area | 7.0361 | 2016-04-25 | 2016-07-27 | 1900-01-04 23:54
| 70 | C-88-011-14 | Street for Cycling-Project #1 at Various Locations | 4.1 | 2016-05-12
| 71 | C-88-004-15 | Bridge/Viaduct Painting Project #6 at various locations | 1.5 | 2016-05-24
| 72 | C-88-005-15 | Bridge/Viaduct Painting -Project #5 at various locations | 1.5 | 2016-05-24
| 73 | C-88-048-12 | Grand Avenue; Pulaski Rd to Chicago Ave Road Reconstr | 16 | 2016-06-17
| 74 | C-88-016-10 | Various Pedestrian Improvements | 1.6525 | 2016-06-23
| 75 | C-88-027-13 | Oakwood Blvd over Metra/ICC - Reconstruction viaduct | 15.6862 | 2016-09-16
| 76 | C-88-006-15 | Citywide commuter bike parking and promotion | 2.4524 | 2016-09-21
#REF! | ** Information sorted by Approved date
| 76 |  |  | 871.873 |  |  |  |  | 767.9651
Note on J24: (up to $65M)

## 2020 Additions
# | State | County | State Contract # | Description | Cost (M) est. | Approved** | Award | Award Cost (M) | Column3 | Omisison Reason | State | Total | Projects
375 | CA | Los Angeles & Orange | HD-S3009 | Coastal Bike Trail Connector at Ocean Boulevard | 16 | 2020-03-24 |  |  |  |  | CA | 77.7 | 4
421 | CA | Los Angeles & Orange | HD-S2556 | Gerald Desmond Bridge Demolition | 44.2 | 2020-10-02 |  |  |  |  | IL | 669.19 | 50
435 | CA | Contra Costa | ATPL 5928(151) | Fred Jackson 1st/Last mile complete streets construction | 2.9 | 2020-12-18 |  |  |  |  | MN | 15.23 | 8
436 | CA | Contra Costa | BRLS-5928(128) | Marsh Drive bridge over Walnut Creek replacement | 14.6 | 2020-12-18 |  |  |  |  | NV | 200 | 1
371 | IL | Peoria | 68C98 | IL-6 ramp resurfacing | 13 | 2020-01-28 |  |  |  |  | NY | 253.7 | 4
372 | IL | Woodford | 68E24 | I-39 resurfacing | 10.5 | 2020-01-28
373 | IL | Montgomery | 72D31 | I-55 resurfacing & structure rehabilitation | 23.98 | 2020-01-28
374 | IL | Lawrence | 74411 | IL-1 pavement rehabilitation | 6.29 | 2020-01-28
376 | IL | Cook | 62A76 | I-90/I-94 Northbound Reconstruction | 47.91 | 2020-03-13
377 | IL | Cook | 62A77 | I-90/I-94 Southbound Reconstruction | 47.95 | 2020-03-13
378 | IL | Rock Island | 64J28 | IL-5 resurfacing | 5 | 2020-03-13
379 | IL | Boone & Winnebago | 64N36 | US 20 dowel bar retrofit | 7 | 2020-03-13
380 | IL | Peoria | 68A81 | IL-29 resurfacing | 9.6 | 2020-03-13
381 | IL | Logan | 72E23 | I-155 resurfacing | 7.5 | 2020-03-13
382 | IL | Sangamon | 72G46 | I-55 resurfacing | 19.68 | 2020-03-13
383 | IL | Christian | 72G70 | IL-29 resurfacing | 7.1 | 2020-03-13
384 | IL | Sangamon | 72H51 | I-72 bridge deck replacement | 7.5 | 2020-03-13
385 | IL | Cumberland | 74542 | US 40 pavement rehabilitation | 5.51 | 2020-03-13
386 | IL | Macon | 74779 | US 51 pavement rehabilitation | 13.96 | 2020-03-13
387 | IL | Effingham | 74907 | US 45 pavement rehabilitation | 5.68 | 2020-03-13
388 | IL | Macon | 74917 | Old Route 36 pavement rehabilitation | 7.79 | 2020-03-13
392 | IL | Randolph | 76J71 | IL-3 Resurfacing, ADA & storm sewer improvements | 7.8 | 2020-05-01
395 | IL | Jersey | 76568 | US 67 expressway construction | 24 | 2020-06-09
396 | IL | Vermillion | 70A92 | I-74 superstructure replacement | 17.8 | 2020-06-09
397 | IL | Jefferson | 78600 | I-57 resurfacing | 7.6 | 2020-06-09
398 | IL | Williamson | 78787 | I-57 resurfacing | 9 | 2020-06-09
399 | IL | Peoria | 68F15 | I-74 resurfacing | 15 | 2020-06-25
400 | IL | Macon | 74710 | 19th Street pavement rehabilitation | 5.7 | 2020-06-25
401 | IL | Henderson | 68F21 | IL-64 resurfacing | 5.8 | 2020-06-25
403 | IL | Cook | 60P14 | IL-72 & IL-83 Intersection Improvements | 5.14 | 2020-08-11
404 | IL | Lake | 62B65 | New pump station | 11.8 | 2020-08-11
405 | IL | Winnebago | 64L14 | US 20 intersection improvements | 6.2 | 2020-08-11
406 | IL | Madison | 76H84 | I-70, I-270, I-55/70 resurfacing | 21 | 2020-08-11
407 | IL | Greene & Jersey | 76L20 | US 67 resurfacing | 4.4 | 2020-08-11
408 | IL | Will | 60W34 | I-80 eastbound resurfacing/widening | 41.2 | 2020-09-17
409 | IL | McHenry | 62A80 | IL-47 at Kishwaukee River structure replacement | 7.1 | 2020-09-17
410 | IL | Will | 62M63 | I-55 at IL-59 interchange reconstruction | 11 | 2020-09-17
411 | IL | Rock Island | 64F78 | I-280 resurfacing and deck replacement | 40 | 2020-09-17
412 | IL | Ford | 66K20 | IL-9 resurfacing | 6.6 | 2020-09-17
413 | IL | Warren | 68D95 | US 34 structure replacement | 5.2 | 2020-09-17
414 | IL | McLean | 70A65 | Veterans Parkway (FAP 704) resurfacing | 6.5 | 2020-09-17
415 | IL | Adams | 72L58 | US 24 Memorial Bridge rehabilitation | 12 | 2020-09-17
416 | IL | St. Clair | 76B55 | I-70 structure rehabilitation | 35.4 | 2020-09-17
417 | IL | Wayne | 74982 | I-64 pavement rehabilitation | 7.3 | 2020-09-17
418 | IL | Franklin | 78481 | IL-149 pavement reconstruction & resurfacing | 3.8 | 2020-09-17
419 | IL | Pulaski | 78785 | Old US 51 (FAS 2936) resurfacing | 9 | 2020-09-17
420 | IL | Vermillion | 90922 | Tilton Road over I-74 structure replacement | 4.5 | 2020-09-17
427 | IL | Will | 62M06 | I-55 resurfacing | 12.4 | 2020-11-18
428 | IL | Winnebago | 64H08 | US 20 BUS (W. State St.) roadway reconstruction | 8 | 2020-11-18
429 | IL | Madison | 76M48 | Resurfacing on IL 157 | 4.8 | 2020-11-18
430 | IL | Madison | 76M84 | Resurfacing on IL 159 | 8.5 | 2020-11-18
431 | IL | Shelby & Macon | 74549 | Rehabilitation on US 51 | 7.1 | 2020-11-18
432 | IL | Macon | 74757 | I-72 reconstruction | 28.7 | 2020-11-18
433 | IL | Massac | 78606 | I-24 bridge repair and resurfacing | 22.9 | 2020-11-18
389 | MN | St. Louis | SP-069-060-002 | CSAH-61 French River Wayside Rest Area Reconstruction | 1.1 | 2020-03-31
390 | MN | St. Louis | SP-069-090-033 | Mesabi Trail - TH 169 Underpass to CSAH 88 | 0.9 | 2020-03-31
391 | MN | St. Louis | SP-069-643-017 | CSAH 43 pavement rehabilitation | 3.1 | 2020-03-31
422 | MN | St. Louis County | SP 069-605-049 | CSAH 5 pavement rehabilitation & resurfacing | 1.44 | 2020-11-04
423 | MN | St. Louis County | SP 069-629-007 | CSAH 29 pavement rehabilitation & resurfacing | 3.4 | 2020-11-04
424 | MN | St. Louis County | SP 069-656-018 | CSAH 56 pavement rehabilitation & resurfacing | 2.65 | 2020-11-04
425 | MN | St. Louis County | SP 069-665-008 | CSAH 65 bridge replacement | 1.2 | 2020-11-04
426 | MN | St. Louis County | SP 069-716-012 | CSAH 116 resurfacing | 1.44 | 2020-11-04
437 | NV | Clark |  | I-15 Tropicana Avenue Interchange Reconstruction | 200 | 2020-12-22
393 | NY | Otsego & Schoharie | PIN 93588.22 | I-88 Resurfacing & Bridge Rehabilitation | 43.2 | 2020-04-17
394 | NY | Ulster | PIN 8808.62/ D264169 | Wurts Street bridge rehabilitation | 38.7 | 2020-04-20
402 | NY | Queens | PIN X735.80 D264076 | Van Wyck Expressway Viaduct Deck Replacement | 144 | 2020-07-27
434 | NY | Westchester | PIN 8813.68 / D264324 | Westchester County Bridge Rehabilitation (4 bridges) | 27.8 | 2020-11-17
67 |  |  |  |  | 1215.82